AEROSYS AVIONICS SYSTEMS LTD.

AeroSys 9000 Integrated Avionics Platform

SOFTWARE DEVELOPMENT PLAN

(SDP)

| Document Number | AEROSYS-SDP-001 |
| --- | --- |
| Revision | A — Initial Release |
| Date | 2026-03-14 |
| DO-178C Level | DAL B/C/D/E |
| Classification | PROPRIETARY — RESTRICTED |

# 1  Purpose and Scope

This Software Development Plan (SDP) describes the development activities, standards, methods, environment, and processes that will be used to develop the AeroSys 9000 software. It satisfies DO-178C Section 11.2 and is referenced by the PSAC (AEROSYS-PSAC-001).

## 1.1  Life Cycle Model

A sequential waterfall model with approved feedback loops is used. All phase entries require satisfaction of the transition criteria defined in AEROSYS-PSAC-001 Section 4.2.

# 2  Development Environment

## 2.1  Hardware

| Item | Specification | Role |
| --- | --- | --- |
| Development Host | x86-64 Linux workstation, 32GB RAM | Build, unit test, formal proof |
| Simulation Target | Raspberry Pi 5 (ARM Cortex-A76) | Integration test, timing measurement |
| Coverage Host | Same as dev host with gcov/lcov | Structural coverage analysis |
| CM Server | Dedicated Git server (on-prem) | Authoritative baseline storage |

## 2.2  Software Tools

| Tool | Version | DO-330 TQL | Purpose |
| --- | --- | --- | --- |
| GNAT Pro | 24.0 | TQL-5 | Ada 2022 compiler — primary development tool |
| GNATprove | 24.0 | TQL-1 | SPARK 2014 formal prover (DAL B/C) |
| GNATcoverage | 24.0 | TQL-1 | MC/DC and statement/branch coverage |
| GNATtest | 24.0 | TQL-5 | Unit test skeleton generation |
| GNATcheck | 24.0 | TQL-5 | Coding standard enforcement |
| GNATstack | 24.0 | TQL-1 | Worst-case stack depth analysis |
| gprbuild | 24.0 | TQL-5 | Deterministic build system |
| AUnit | 24.0 | TQL-5 | Ada unit test framework |
| Git | 2.43 | TQL-5 | Configuration management |
| Jenkins | 2.449 | TQL-5 | CI/CD — automated build + test pipeline |
| DOORS NG | 6.0 | TQL-5 | Requirements management + traceability |

## 2.3  SPARK 2014 Formal Verification

DAL B components (FADEC interface, autopilot engagement, TCAS processing) and selected DAL C components (ARINC 429 decode layer) are implemented in the SPARK 2014 subset of Ada 2022. GNATprove is used to prove:

- Absence of runtime errors (ATC — run-time check mode)

- Information flow correctness (all Depends contracts discharged)

- Functional correctness (all Pre/Post contracts proved)

- Loop termination (Loop_Variant pragmas in all loops)

GNATprove run command for CI:

gnatprove -P aerosys.gpr --level=4 --mode=prove --prover=z3,cvc5,altergo --timeout=60 --checks-as-errors --proof-warnings

# 3  Coding Standards

## 3.1  DAL B — SPARK 2014 Subset

All DAL B source files must carry pragma SPARK_Mode(On) and satisfy:

- No dynamic storage allocation (no Ada.Unchecked_Deallocation, no access type allocators)

- No recursive subprogram calls (call graph must be acyclic — verified by GNATcheck)

- No uninitialized variables (GNATprove enforces this in proof mode)

- All subprograms have explicit Global and Depends aspects

- All public subprograms have Pre and Post contracts

- All loops have Loop_Invariant and Loop_Variant pragmas

- Exceptions may not propagate across package boundaries — all exceptions handled locally

- No use of System.Address arithmetic

- Maximum cyclomatic complexity per subprogram: 10

- Maximum subprogram body length: 100 lines

## 3.2  DAL C — Ada 2022 Safety Subset

DAL C files carry pragma SPARK_Mode(Off) but must comply with the GNATcheck AEROSYS-CODING ruleset, which enforces:

- No dynamic allocation (same as SPARK subset)

- No recursion (same)

- All objects given explicit initial values in declarations

- All exception handlers must be documented with a comment stating the recovery action

- Fixed-size string buffers only (String(1..N) constraints, no Ada.Strings.Unbounded in safety paths)

- Maximum cyclomatic complexity: 15

- Maximum subprogram length: 200 lines

- No access type dereferences without null check

## 3.3  DAL D/E — JavaScript (Vercel Layer)

The Vercel serverless layer (DAL D/E) must comply with the AEROSYS ESLint configuration. Key rules:

- No eval() or Function() constructor

- No var declarations — use const/let only

- All async functions must have explicit error handling

- No process.exit() in production handlers

- All API inputs validated before use

# 4  Review Process

| Review Type | Trigger | Reviewers | Checklist |
| --- | --- | --- | --- |
| Software Requirements Review | SRS baseline | Lead Eng + DER + QA | AEROSYS-CL-001 |
| Preliminary Design Review | SDD 50% complete | Lead Eng + Safety + QA | AEROSYS-CL-002 |
| Critical Design Review | SDD baseline | Lead Eng + DER + QA | AEROSYS-CL-003 |
| Code Review | Each module complete | Peer (≠ author) + QA | AEROSYS-CL-004 |
| Test Readiness Review | LLT procedures complete | Test Lead + QA | AEROSYS-CL-005 |
| Certification Readiness Review | All tests complete | DER + QA + Mgmt | AEROSYS-CL-006 |

Independence requirement: the reviewer of any artifact must not be the original author of that artifact.

# 5  Traceability

Bidirectional traceability shall be maintained in DOORS NG throughout the life cycle:

- System Requirements → HLRs (SRS): each system requirement covered by ≥1 HLR

- HLRs → LLRs (SDD): each HLR derived into ≥1 LLR

- LLRs → Source Code: each LLR implemented in ≥1 identified code module/subprogram

- Source Code → Test Cases: each code element exercised by ≥1 test case

- Test Cases → Test Results: each test case has a pass/fail result in SVTR

Traceability gaps discovered at any phase shall be raised as Problem Reports and resolved before the next phase transition.

# 6  Development Schedule

| Phase | Start | End | Key Entry Criterion | Key Exit Criterion |
| --- | --- | --- | --- | --- |
| HLR Development | 2026-06-01 | 2026-10-01 | PSAC approved | SRS Rev A baselined |
| LLR + Architecture | 2026-10-01 | 2027-03-01 | SRS baselined | SDD Rev A baselined |
| Coding — DAL B | 2027-03-01 | 2027-09-01 | SDD baselined | SPARK proofs passing |
| Coding — DAL C/D | 2027-06-01 | 2027-12-01 | SDD baselined | GNATcheck clean |
| Unit Testing (LLT) | 2027-09-01 | 2028-06-01 | Code baseline | MC/DC achieved |
| Integration Testing | 2028-03-01 | 2028-12-01 | LLT complete | All HLTs passed |
| SAS Preparation | 2028-12-01 | 2029-03-01 | All tests complete | SAS submitted |